## Sheet1
Systems Development Action Plan
Project Title : Development of PPEI Website
Project Duration : October 10, 2017 - January 10, 2018
ACTIVITIES | TARGET | No. of Days | OUTPUT | DETAILS | RESPONSIBLE PERSON(S)
Requirements gathering | Week 1 | 3 | User requirements & Development Tools | List of System Features & list of Development Tools | Developers / ISTMS
Systems analysis and design | Week 1-2 | 5 | Draft Documentation | Draft Data Flow Diagram, Entity Relationship Diagram, Use Case Diagram, Process Flow, Database Schema, Gantt Chart, Work breakdown schedule | Developers
Presentation to PPEI & ISTMS | Week 2 | 1 | Critiqued Draft Documentation | Final Data Flow Diagram, Entity Relationship Diagram, Use Case Diagram, Process Flow, Database Schema, Gantt Chart, Work breakdown schedule, List of modules and assigned programmer | Developers / ISTMS
Actual coding | Week 2 - 4 | 11 | System Prototype (50%) | System prototype and 50% of user requirements accomplished | Developers
Presentation of Accomplishment to PPEI / ISTMS | Week 5 | 1 | Revisions | Revisions based on the presented prototype | PPEI / ISTMS / DEVELOPERS
Modification base on comments | Week 5 | 4 | System Prototype (50%) | Polished 50% of user requirements | Developers
Configuration and deployment to server | Week 6 | 1 | Website is accessible | Initiate a request to NTMD for the hosting of the system. Website is deployed to server. Website has been tested and properly configured. | Developers / NTMD /ISTMS
Actual coding | Week 6 - 7 | 5 | System Prototype (80%) | 80% of user requirements accomplished | Developers
Presentation of Accomplishment to ISPDPMD | Week 7 | 1 | Revisions | List of minor revisions | PPEI / ISTMS
Modification base on comments | Week 7 | 2 | System Prototype (80%) | Polished 80% of user requirements | Developers
Actual coding | Week 7 - 8 | 6 | System Prototype (100%) | 100% of user requirements accomplished | Developers
Presentation of Accomplishment to ISPDPMD | Week 9 | 1 | Revisions | List of minor revisions | PPEI / ISTMS / DEVELOPERS
Modification base on comments | Week 9 | 2 | System Prototype (100%) | Furnished 100% of user requirements | Developers
Draft documentation and user manual | Week 9-10 | 5 | Updated Documentation | Draft documentation and user manual | Developer
Testing and evaluation | Week 10 | 2 | Bug List checklist | List of identified bugs / errors. | Developers/PPEI/ISTMS
Finalize documentation and user manual | Week 11 | 2 | Finalized Documentation | Documentation and user manual | Developers
Final presentation to client | Week 11 | 1 | Acceptance Certificate | Acceptance Certificate | PPEI / Developers
Bug fixing | Week 11-12 | 4 | Resolved Bug List checklist | 100% bug fixed | Developers
Preparation of full documentation for book binding | Week 12 | 2 | Hard copy of system documentation | Complete hard / soft bound documentation | Developers
User training and orientation / Traning of Trainors | Week 12 | 1 | List of Trained Users Accomplished Website Usability Survey Forms | List of trained users and website usability survey | Developer / PPEI